## Sheet1
STT | Task | Status | Deadline | Design | Backend | Frontend | Test | Release | Correspoding API | Người chịu trách nhiệm | Môi trường code | Môi trường test API | Ghi Chú | Đã push code lên master | Hoàn thành
1 | Login | 50% | 23:59 15/7/2022 | 100% | 100% | 0% | 0% | 0% | Backend only | An | Eclipse | None | Lỡ tay xoá mất source code do Push và Commit sai | FALSE | FALSE
2 | Logout | 50% | 23:59 15/7/2022 | 100% | 50% | 0% | 0% | 0% | Backend only |  | Eclipse | None | Lỡ tay xoá mất source code do Push và Commit sai | FALSE | FALSE
3 | Create product | 30% | 12:00 22/7/2022 | 100% | 50% | 0% | 0% | 0% | Product API | Hoàng Kim Phú+Lộc | Eclipse | Postman |  | FALSE | FALSE | Môi Trường Chung
4 | View a specific product | 30% | 12:00 22/7/2023 | 100% | 50% | 0% | 0% | 0% | Product API |  | Eclipse | Postman |  | FALSE | FALSE | Eclipse | version anh Trung đã hướng dẫn sử dụng
5 | Delete a specific product | 30% | 12:00 22/7/2024 | 100% | 50% | 0% | 0% | 0% | Product API |  | Eclipse | Postman |  | FALSE | FALSE | MSSQL | 14 trở lên
6 | Update a specific product | 30% | 12:00 22/7/2025 | 100% | 50% | 0% | 0% | 0% | Product API |  | Eclipse | Postman |  | FALSE | FALSE | Java maven dependencies | 2.7.0 May, 2022
7 | Create promotion | 0% | Updating | 0% | 0% | 0% | 0% | 0% | Promote API | Hiếu+Lộc |  |  | Chưa quyết định | FALSE | FALSE | Visual Studio | từ Version 16.1 trở lên
8 | View a specific promotion | 0% |  | 0% | 0% | 0% | 0% | 0% | Promote API |  |  |  |  | FALSE | FALSE | HTML 5 | mới nhất tính tới 14/6/2022
9 | Delete a specific promotion | 0% |  | 0% | 0% | 0% | 0% | 0% | Promote API |  |  |  |  | FALSE | FALSE | CSS 3 | mới nhất tính tới 14/6/2022
10 | Update a specific promotion | 0% |  | 0% | 0% | 0% | 0% | 0% | Promote API |  |  |  |  | FALSE | FALSE | Bootstrap | mới nhất tính tới 14/6/2022
11 | View order list | 25% | 12:00 22/7/2022 | 100% | 20% | 0% | 0% | 0% | Order API | Khanh+Lộc | Eclipse | Postman |  | FALSE | FALSE
12 | View order detail | 25% | 12:00 22/7/2022 | 100% | 20% | 0% | 0% | 0% | Order API |  | Eclipse | Postman |  | FALSE | FALSE
13 | Update order | 25% | 12:00 22/7/2022 | 100% | 20% | 0% | 0% | 0% | Order API |  | Eclipse | Postman |  | FALSE | FALSE
14 | Delete order | 25% | 12:00 22/7/2022 | 100% | 20% | 0% | 0% | 0% | Order API |  | Eclipse | Postman |  | FALSE | FALSE
15 | Add manufactuer | 50% | 12:00 15/7/2022 | 100% | 100% | 50% | 0% | 0% | Manufacturer API | Duy+Lộc+Hiếu | Eclipse | Postman |  | FALSE | FALSE
16 | Edit manufacturer | 50% | 12:00 15/7/2023 | 100% | 100% | 50% | 0% | 0% | Manufacturer API |  | Eclipse | Postman |  | FALSE | FALSE | unit test junit | test
17 | View manufacturer | 50% | 12:00 15/7/2024 | 100% | 100% | 50% | 0% | 0% | Manufacturer API |  | Eclipse | Postman |  | FALSE | FALSE
18 | Delete manufacturer | 50% | 12:00 15/7/2025 | 100% | 100% | 50% | 0% | 0% | Manufacturer API |  | Eclipse | Postman |  | FALSE | FALSE
19 | Search manufactuer | 50% | 12:00 15/7/2026 | 100% | 100% | 50% | 0% | 0% | Manufacturer API |  | Eclipse | Postman |  | FALSE | FALSE
20 | Add to cart | 30% | 12:00 15/7/2022 | 100% | 20% | 0% | 0% | 0% | Cart API | Sáng+Lộc | Eclipse | Postman |  | FALSE | FALSE
21 | View cart | 30% | 12:00 15/7/2022 | 100% | 20% | 0% | 0% | 0% | Cart API |  | Eclipse | Postman |  | FALSE | FALSE
22 | Update cart | 30% | 12:00 15/7/2022 | 100% | 20% | 0% | 0% | 0% | Cart API |  | Eclipse | Postman |  | FALSE | FALSE
23 | Checkout | 30% | 12:00 15/7/2022 | 100% | 20% | 0% | 0% | 0% | Cart API |  | Eclipse | Postman |  | FALSE | FALSE
24 | Search by category | 30% | 12:00 15/7/2022 | 100% | 20% | 0% | 0% | 0% | Cart API |  | Eclipse | Postman |  | FALSE | FALSE
25 | Search by name | 30% | 12:00 15/7/2022 | 100% | 20% | 0% | 0% | 0% | Cart API |  | Eclipse | Postman |  | FALSE | FALSE
26 | Add category | 75% | 12:00 15/7/2022 | 100% | 100% | 100% | 0% | 0% | Category API | Cả team cùng code bài mẫu | Eclipse/intellij | Postman |  | TRUE | FALSE
27 | View category | 75% | 12:00 15/7/2022 | 100% | 100% | 100% | 0% | 0% | Category API |  | Eclipse/intellij | Postman |  | TRUE | FALSE
28 | Update category | 75% | 12:00 15/7/2022 | 100% | 100% | 100% | 0% | 0% | Category API |  | Eclipse/intellij | Postman |  | TRUE | FALSE
29 | Delete category | 75% | 12:00 15/7/2022 | 100% | 100% | 100% | 0% | 0% | Category API |  | Eclipse/intellij | Postman |  | TRUE | FALSE
30 | Frontend | 0% | 23:59 30/6/2022 | [6 empty] | Lộc | Eclipse |  | Bootstrap + hỗ trợ các thành viên khác | FALSE | FALSE
31 | Database manager | 100% | 12:00 17/6/2022 | [6 empty] | Cả Team | MSSQL |  | Trễ Deadline | FALSE | TRUE
32 | SRS | 100% | 12:00 24/6/2022 | [6 empty] | An + Sáng | Word |  | Trễ Deadline, thiếu Class Diagram (đã hoàn thành) | FALSE | TRUE
33 | Git manager | [8 empty] | An |  |  |  | FALSE | FALSE